## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Fix update study set | Can not update study set when changing study set | 1 | https://quizletclone.atlassian.net/jira/software/projects/QUIZ/issues/QUIZ-1?filter=doneissues&referrer=agility | Closed | VuBL | 2023-02-06 21:32 | 2/8/2023 23:59:59 PM | iter2 | Task, 3_Done | Study set
Fix animation card in study set | Fix animation when view flash cards in study set | 2 | https://quizletclone.atlassian.net/jira/software/projects/QUIZ/issues/QUIZ-3?filter=doneissues&referrer=agility | Closed | VuBL | 2023-02-06 21:32 | 2/12/2023 23:59:59 PM | iter2 | Task, 3_Done | Flash Cards
Bug send email | Get code from send email to active account to login | 3 | https://quizletclone.atlassian.net/jira/software/projects/QUIZ/issues/QUIZ-7?filter=doneissues&referrer=agility | Closed | VuBL | 2023-02-08 17:04 | 2/12/2023 23:59:59 PM | iter2 | Task, 3_Done | Verify
Create folder UI | Create folder UI can not merge to CSS | 4 | https://quizletclone.atlassian.net/jira/software/projects/QUIZ/issues/QUIZ-16?filter=doneissues&referrer=agility | Closed | VuBL | 2023-03-06 05:00 | 2023-03-12 16:45 | iter3 | Task, 3_Done | Folder
Create class UI | Create class UI can not merge to CSS | 5 | https://quizletclone.atlassian.net/jira/software/projects/QUIZ/issues/QUIZ-17?filter=doneissues&referrer=agility | Closed | VuBL | 2023-03-06 05:01 | 2023-03-12 16:45 | iter3 | Task, 3_Done | Class